## 90-Day Plan
Taveat Solutions: 90-Day Launch Plan
Start date (Monday): |  | 2026-11-02 | Change this date and every week's date updates.
Weeks done: |  | 0% | How to use: yellow cells are yours to fill in. Set "Done?" to Yes when the week's goal is met.
Week | Week of | Phase | Focus | Build (agents and tools) | Sell | Deliver to clients | End-of-week goal | Done? | Notes
1 | 2026-11-02 | 1. Get ready | Finish the setup | Run the updated Airtable setup. Reconnect the Process Mapper's Airtable step. Import the Opportunity Scorer and test both end to end. | Pick your industry (recommended: Shopify brands). List 50 target businesses. Tailor the sales sheet to that industry. | None yet | Both agents save to Airtable | No
2 | 2026-11-09 | 1. Get ready | Practise the audit | Copy the audit report template into Google Docs. Build the leak calculator spreadsheet (formulas in PROFIT_LEAK_AUDIT.md). | Recruit 2 to 3 friendly businesses for a free practice audit. Start posting 3 times a week (LinkedIn or Instagram). | Practice audit 1: calls and maps | First practice audit report finished | No
3 | 2026-11-16 | 1. Get ready | Spec Writer + outreach | Build the Spec Writer agent (F-1). | Message 10 target businesses a day. Ask practice businesses for testimonials. | Practice audits 2 and 3 | 2 testimonials, 5 sales calls booked | No
4 | 2026-11-23 | 1. Get ready | QA Agent (short week: Thanksgiving) | Build the QA Agent (F-3). Phase 1 agents complete. | Hold sales calls. Offer the $497 paid audit. | None | 4 agents running, first paid audit sold | No
5 | 2026-11-30 | 2. First revenue | First paid audit | Set up basic monitoring: n8n error alerts to Slack or email. | Keep up outreach and sales calls. | Paid audit 1 | First $497 earned, package recommended | No
6 | 2026-12-07 | 2. First revenue | Close the first client | Turn the instant lead reply and review request automations into reusable templates. | Convert audit 1 into a package. Sell audit 2. | Paid audit 2 | First package signed | No
7 | 2026-12-14 | 2. First revenue | Quick win for client 1 | Build the Insight tools: customer groups (best, at risk, lapsed) from a Shopify export. | Push the founding-client offer (30% off for a case study). | Client 1 setup: quick win live within 14 days | Client 1 sees a result | No
8 | 2026-12-21 | 2. First revenue | Holiday week (light) | Build the pricing and product analysis template. | Holiday posts. Book January sales calls. | Client 1 setup continues | Client 1 fully live | No
9 | 2026-12-28 | 3. Insight and ads | Holiday week: practise ads | Practise with Higgsfield: make 10 ads for a sample product. Set up a brand in Ads Studio. | Plan January outreach. | Monitoring only | Ad-making process tested | No
10 | 2027-01-04 | 3. Insight and ads | Monthly reporting | Build the win-back campaign template. Draft the Value Reporter agent (M-3). | Restart outreach. Run audits 3 and 4. | Client 1's first monthly report. Onboard client 2. | 2 paying clients | No
11 | 2027-01-11 | 3. Insight and ads | First Insight client | Build the Monitor agent (M-1) properly. | Pitch the Insight upgrade to client 1. Run audit 5. | Client 2 setup. Insight work begins. | First Insight client in setup | No
12 | 2027-01-18 | 3. Insight and ads | First Growth Partner pitch | Build the weekly ad performance report template. | Pitch Growth Partner to a prospect spending $3K+ a month on ads. | Client 2 quick win. Insight dashboard delivered. | 3 clients signed | No
13 | 2027-01-25 | 4. Review | 90-day review | Choose the next agents to build (A-2, A-3, F-4), based on which manual work hurts most. | Turn client 1's results into a case study. Update the sales sheet. | Monthly reports for all clients | Review the Scoreboard and set the next 90 days | No
Formulas:
Week of = C2+7*([Week]-1)

## Scoreboard
Scoreboard: targets at day 30, 60 and 90
Fill in the yellow Actual cells. Status updates on its own. Targets are cumulative (totals so far).
Measure | Day 30 target | Day 30 actual | Day 30 status | Day 60 target | Day 60 actual | Day 60 status | Day 90 target | Day 90 actual | Day 90 status | Why this target
Agents running | 4 |  |  | 4 |  |  | 6 |  |  | Phase 1 (4 agents) by week 4; Monitor and Value Reporter by week 11
Practice audits done | 3 |  |  | 3 |  |  | 3 |  |  | Practice on friendly businesses before charging
Paid audits sold | 1 |  |  | 3 |  |  | 5 |  |  | About 1 every 2 weeks once outreach is steady
Sales calls held | 5 |  |  | 12 |  |  | 20 |  |  | Assumes 10 outreach messages a day
Clients signed | 0 |  |  | 1 |  |  | 3 |  |  | Assumes about half of paid audits convert (audit guide target)
Monthly recurring revenue ($) | 0 |  |  | 750 |  |  | 3250 |  |  | Example mix at day 90: 1 Insight ($1,750) + 2 Foundation ($750 each), list prices before founding discount
Testimonials or case studies | 2 |  |  | 2 |  |  | 3 |  |  | From practice audits first, then client 1

## Rules
Rules for running this plan solo
1 | Build an agent only when doing that job by hand starts costing you real time.
2 | Never set up more than 2 clients at the same time.
3 | Take on at most 3 Growth Partner clients while you're solo.
4 | Spend about 30% of your week on sales and marketing, every week.
5 | If you're behind on clients, spend spare time on outreach, not on building more agents.
6 | Tell Growth Partner clients that real ad results arrive around month 3.
7 | First hire (at about 6 to 8 clients): a part-time ad editor or assistant.